## Slide 1: Fiscal Year 2025 Implementation Work Plan April 2024 DRAFT
Jackson & Teton County Long Range Planning
Comp Plan ITP Housing Action Plan Approved: INSERT DATE

## Slide 2: Introduction
The Jackson/Teton County Comprehensive Plan (Comp Plan), Integrated Transportation Plan (ITP), and Housing Action Plan (HAP) are adopted, and staff structures are in place to implement each plan.
Implementation of the policies and strategies in the three plans is a fulltime workload for the individual departments and advisory boards responsible for each plan.
This Work Plan for the 2025 fiscal year (FY 25 Work Plan) presents projects together from all three plans that require coordination between departments to illustrate the workload on those responsible for them all – the public, Town and County planners, Town and County Public Works, Housing Department, the Board of County Commissioners, and Town Council.

## Slide 3: Purpose
The purpose is to present all the community’s upcoming coordinated planning projects for land use, transportation, and housing in one place so that the Board of County Commissioners and Town Council can prioritize their efforts, direct fiscal resources, and set expectations for the public on upcoming projects. Each “Task” in this Work Plan corresponds to completing one or more strategies in the Comprehensive Plan, Integrated Transportation Plan or Housing Action Plan—tying broad community visions and values to action items and results. The strategy numbers listed throughout this Work Plan reference Strategies listed in the 2020 updated Comp Plan.
Community Vision
Common Values
Principles
Policies
Strategies
=
Work Plan Tasks

## Slide 4: Scope
This FY25 Work Plan identifies tasks that rely on coordinated planning resources through fiscal year 2025 (ending June 2024) and beyond.
Tasks from the Integrated Transportation Plan and Housing Action Plan carried out by Town/County Public Works or the Housing Department beyond the coordinated planning stages are not included in this Work Plan but are represented in Work Plans for those departments.
This Work Plan proposal was developed by staff to reflect interests of the Board of County Commissioners and Town Council but is presented as a draft with the expectation that joint discussion between the Board and Council may result in amendment of the Plan prior to approval. This Work Plan can be revisited and revised jointly throughout FY25 as necessary if staff or fiscal resources change or if priorities shift.

## Slide 5: Staff Capacity
This proposed Work Plan is based on existing Long-Range Planning staffing levels which include:
Joint Town and County Long-Range Principal Planner
Joint Associate Long-Range Planner (ASSUMED VACANT)
County Associate Long-Range Planner
If the County or Town adds positions, or has vacant staff positions, this Work Plan can be revisited to expand and/or contract associated work tasks.
Similarly, if other departments have staff with this expertise, that have hours of availability to contribute this work plan, that would be another opportunity to accomplish and/or expand the work tasks in this Work Plan.

## Slide 6: FY25 Long Range Planning Priorities
In addition to annual and ongoing tasks listed in this Work Plan, the Town and County work together to prioritize joint long-range planning tasks each fiscal year.
The Town and County will also each individually prioritize Town-only and County-only long-range planning tasks. The following joint, Town-only, and County-only tasks are recommended for prioritization by staff for the coming fiscal year, in addition to the ongoing and annual tasks that consume time and resources.

## Slide 7: Work Plan Tasks
Each task is represented by an individual chart and narrative. The “progress” measure is the percent of task completion at the time this Work Plan was drafted.
In the “resources” fields, amounts under FY 25 are estimated staff hours and costs for consultant services by the end of June 2025 (which may be more or less than what was initially budgeted). For years prior to FY 24, those values are for time/money actually spent (which may be more or less than what was initially budgeted).
Any estimated values can be updated once the 2024 Fiscal Year has ended, and the 2025 Fiscal Year budget has been approved.

## Slide 8: Work Plan Tasks
The Work Plan tasks (beginning on page 12) are organized chronologically based on Fiscal Year and are color-coded by the representative Comprehensive Plan Common Value each task implements.
Achieving our Vision
Quality of Life
Ecosystem Stewardship
Growth Management

## Slide 9: Work Plan Tasks
JOINT TASKS | 
In Progress (and to roll over to FY25) | New (beginning in FY25)
Road and Pathways Standards LDR Update (Pathways) (20% complete) Joint Annual Indicator Report Review (Joint Long Range Planning) (30% complete) | Traffic Impact Study LDRs (Planning)
TOWN TASKS | 
In Progress | New
Hillside LDRs Update (Planning) (on hold) Town Water Quality (Town Public Works & Planning) (70% complete) Town Workforce Housing Mitigation LDRs (Joint LR Planning) (on hold) Ecosystem Indicators (Ecosystem Stewardship) (20% complete) Climate Action Plan (Ecosystem Stewardship) (75% complete) Karns Meadow Master Planning (Ecosystem Stewardship & Parks & Recreation) (60% complete) Large Building and Workforce Housing Bonus Review (Planning) (on hold) Phase I Diversity Equity & Inclusion (Joint Long Range Planning & Community Development) (on hold) | 
COUNTY TASKS | 
In Progress | New
Natural Resource Regulations & Tiered Habitat Mapping (Planning) (80% complete) Wildlife Crossings Master Plan Implementation (Public Works) (30% complete) Water Quality Master Plan (Public Works) (98% complete) County Workforce Housing Mitigation LDRs (Joint LR Planning) (on hold) Highway 22 Capital Multi Modal Transportation Improvement Projects (Public Works & WYDOT) (WYDOT schedule) County Review of Accessory Residential Units (County Planning) (10% complete) Teton County Scenic Preserve Trust RFP Project (County Planning) (70% complete) | Water Quality LDR Amendments (Planning) Aspens Commercial (Planning) Fire Protection Resolution for New Subdivisions – LDRs (Planning) Business Park Legacy Zoning (County only at this time)

## Slide 10: Fiscal Year 24 Tasks
These tasks are currently underway and are anticipated for completion by the end of the 2024 Fiscal Year in June 2024. The bulk of fiscal resources and staff time have already been allocated and used for these efforts and no additional budget or staff time is requested for FY 25.

## Slide 11: Fiscal Year 24 Tasks – Completing Soon
Project | Completion Date | Page Number
Joint Annual Indicator Report Review | Spring of 2024 | 12
County Water Quality Master Planning | May of 2024 | 13

## Slide 12
FY 24
Joint Annual Indicator Report Review
Comp Plan Strategies:
Policy 9.2.a: Monitor indicators annually
Task: Each year the Town and County compile and publish annual indicator data (see ongoing task in workplan below). Staff turnover has made it difficult to train internal staff to complete this in 2021 and 2023, therefore a contract with a local vendor was utilized as needed. Due to ongoing staffing issues, staff requests that the County and Town complete a new Request for Proposals for this task to complete the indicator report and look for opportunity to create a less staff -intensive format such as an online dashboard. Other ideas and methodologies from an outside consultant could be beneficial for the Town Council and Board of County Commissioners to research. It is important to note that this task does not anticipate reinventing the indicators themselves, or changing the methodology for which the data has historically been gathered to ensure that the trends in the data remain valid. Further review of indicators, additional, or revised indicators etc. would need to be completed through the next Comprehensive Plan Update process.
Status: A request for proposals was conducted in November of 2023 and a contract with LegacyWorks Group was approved during the February 12, 2024 Joint Information Meeting. Work on the project is underway with the 2024 Indicator Report and further reformatting and drafting of a new dashboard system will commence spring of 2024.
Progress | 30% Spring of 2024 Long-Range Planning
Timeframe | 
Task Lead | 
Resources | FY 24
Long-Range Planning | 50 hrs
County Planning Director | 5 hrs
Town Manager | 2 hrs
Town Planning Director | 5 hrs

## Slide 13
County Water Quality Master Planning
Comp Plan Strategies:
1.2.S.3: Develop a water quality enhancement plan that includes consideration of additional County funding for water quality and commits to joint Town and County coordination. The plan should include a water quality monitoring program. The plan should also incorporate or complement existing and future source water assessments, source water protection plans, river and lake management plans, watershed management plans, and other water quality protection efforts. Additionally, in partnership with the Teton Conservation District and other applicable partners, develop with all due dispatch a comprehensive wastewater management plan.
Task: In cooperation with partnering entities, Protect our Water Jackson Hole (POWJH), Teton Conservation District (TCD) and the Town of Jackson, Teton County initiated a study and planning effort to shape the current understanding of existing and potential future human-induced threats to both surface water and groundwater quality and develop strategies for reducing impacts. In December 2021 the Commission approved a contract with a water quality consultant team, Trihydro Corporation, to complete a 20-year vision and implementation plan that protects surface water and groundwater resources from future degradation and improves water quality where known degradation is occurring in Teton County. The management plan effort will focus on both the human element of protecting drinking water and the environmental element of protecting water resources. The Plan will provide a clear set of roles and responsibilities for the various local entities that oversee water resources management. The Plan will address management of wastewater, stormwater, and drinking water, as well as surface and groundwater resources. The Plan will identify and characterize known and possible threats to these resources, while outlining detailed mitigation strategies in an Implementation Plan.
Status: Master Plan will be presented to the Board of County Commissioners in May of 2024 for acceptance.
Progress | 98% Completion date May/June 2024 County Public Works |  |  | 
Timeframe |  |  |  | 
Task Lead |  |  |  | 
Resources | FY 22 | FY 23 | FY 24 | Total
County Pro. Services | 325,000 | $841,623 | $446,329 | $1,166,623
County Public Works | 0 hrs | 400 hrs | 1,200 hrs | 1,600 hrs
Town Public Works | 0 hrs | 50 hrs | 100 hrs | 150 hrs
County General Services | 0 hrs | 20 hrs | 10 hrs | 30 hrs
FY 23-24

## Slide 14: Fiscal Year 24-25 Tasks In-Progress
These tasks are currently underway, and work will continue into FY 25 or beyond. FY 25 budget requests may include fiscal resources needed to continue these tasks. No prioritization of these tasks is needed since they were already prioritized in the FY 24 Work Plan, unless there is interest in changing the scope, timeline or resource allocation.

## Slide 15: Fiscal Year 24-25 Tasks In-Progress
Project | Estimated Completion Date | Page Number
Teton County Scenic Preserve Trust RFP | September 2023-TBD | 16
County Natural Resource LDRs – Tiered Habitat Mapping and LDR Update | Summer 2024 | 17
Joint Road and Pathway Standards LDR Update | July 2023- TBD | 18
Wildlife Crossings Master Plan Implementation | Ongoing -2030 | 19
Town Workforce Housing Mitigation LDRs | TBD | 20
County Workforce Housing Mitigation LDRs | TBD | 21
Karns Meadow Master Plan Implementation | Phase I Construction 2025 | 22
Town Climate Action Plan | June 2024 | 23
Town Climate Implementation | July 2024-Ongoing | 24
Highway 22 Capital Multi-Modal Transportation Projects | Ongoing | 25
Develop Comp Plan Indicators for Chapter 1 for Ecosystem Stewardship | 2023-2024 | 26
Town Water Quality Initiatives | Summer 2024 | 27
ITP Transportation Demand Management/Emerging Mobility Plan | TBD | 28
Large Building and Workforce Housing Bonus Review | TBD | 29
County review of Accessory Residential Units | December 2024 | 30
County Safe Streets & Roads for All | December 2025 | 31
Town Hillside LDRs | TBD | 32

## Slide 16
TCSPT Areas of Focus RFP Project
Comp Plan Strategies:
1.4.S.4 – Explore establishment of a dedicated funding source for the acquisition of permanent open space for wildlife habitat protection, scenic vista protection, and agriculture preservation.
1.4.S.6 – Reevaluate the purpose and staffing of the Teton County Scenic Preserve Trust to provide full-time management for the organization and consider the adoption of higher operational standards.
Task: This task is directed by the Teton County Board of County Commissioners 2023-2024 Strategic Plan. Staff has worked on a Request for Proposal (RFP) to utilize consultant services to reevaluate the purpose, operational standards, and staffing of the TCSPT. Staff will need to select a qualified candidate and facilitate the consultant’s review and recommendations for the Trust with the approval of the Board of County Commissioners. The details of this task will become clearer once a consultant is selected.
Status: This project has begun, and an RFP issued. Due to lack of response Staff will re-issue the RFP and spend additional time facilitating the effort.
Progress | September 2023 - Ongoing FY2023 - 2024 Long-Range Planning
Timeframe | 
Task Lead | 
Resources | FY24-25
Long-Range Planning | 130 hrs
County Attorney | 20 hrs
County Planning Director | 10 hrs
Consultant Services | Undetermined
FY 24-25

## Slide 17
County Natural Resource LDRs – Tiered Habitat Mapping & LDR Update
Comp Plan Strategies:
1.1.S.4: Evaluate and amend wildlife protection standards for development density, intensity, location, clustering, permeability, and wildlife-human conflict.
1.1.S.5: Evaluate mitigation standards for impacts to critical habitat and habitat connections and update as needed.
1.1.S.6: Identify areas for appropriate ecological restoration efforts.
1.2.S.1: Evaluate and update natural resource protection standards for waterbodies, wetlands and riparian areas.
1.2.S.2: Evaluate and update surface water filtration standards, focusing on developed areas near important waterbodies.
Task: Finalize the tiered habitat map previously started and drafted in September of 2018. County Planning is under contract with local experts on this project to most efficiently finalize the work that has been completed to date. The effort would at a minimum utilize the vegetation mapping and focal habitat study (completed in 2017) to update the Natural Resources Overlay (NRO) and other natural resource protection standards. Habitat protection will be updated to be a tiered system that is based on relative critical value. Standards and review requirements applicable in various areas will relate to the relative habitat value of the area to contribute to the short and long-term protection of the health of the habitat network. The County will continue the lead on this effort as it has broader applicability in the County. The Town will ultimately adopt those portions relevant in Town but may do so through a later, separate process once the County has refined the standards through its adoption process.
Status: A draft of the Natural Resource Protection amendments was presented for public review on September 28, 2018. The draft amendments were the product of a significant amount of work completed by the Natural Resources Stakeholder Group and five months of public outreach. A contract has been approved and funding is allocated for a consultant to assist County Staff with finalizing the tiered habitat map, GIS layers, and re-release of updated information for adoption. This task has begun and is underway with a contract (EcoConnect Inc). A public release of the updated regulations is anticipated in summer of 2024.
Progress | 80% FY23 County Planning |  |  |  |  |  |  |  | 
Timeframe |  |  |  |  |  |  |  |  | 
Task Lead |  |  |  |  |  |  |  |  | 
Resources | FY 17 | FY 18 | FY 19 | FY 20 | FY22 | FY 23 | FY 24 | FY 25 | Total
Consulting Services (Town) | $3,000 | $7,000 | $0 | $0 | $0 | $0 | $0 | $0 | $10,000
Consulting Services (County) | $22,000 | $43,000 | $0 | $0 | $5,862 | $2,843 | $1,487 | $9,807 | $85,000
Long-Range Planning | 100 hrs | 200 hrs | 200 hrs | 0 hrs | 12 hrs | 80 hrs | 100hrs | 200hrs | 892 hrs
County Planning Director | 20 hrs | 80 hrs | 80 hrs | 0 hrs | 0 hrs | 0 hrs | 10hrs | 20hrs | 210 hrs
Town Planning Director | 0 hrs | 0 hrs | 0 hrs | 0 hrs | 0 hrs | 0 hrs | 4hrs | 4hrs | 8hrs
County Planning | 100 hrs | 400 hrs | 400 hrs | 0 hrs | 4 hrs | 10 hrs | 20hrs | 20hrs | 954 hrs
County Public Works | 0 hrs | 0 hrs | 0 hrs | 0 hrs | 0 hrs | 0 hrs | 4hrs | 4hrs | 8 hrs
FY 24-25

## Slide 18
Joint Road and Pathway Standards LDR Update
Comp Plan Strategies:
7.1.S.2 Consider adopting “complete streets” and/or “context-sensitive” policies and updated road design standards for all roadways.
Task:. Update LDRs for pathway and county road dimensions and geometric standards and guidance with the intent of making them context sensitive to meet the goals of the community.
Status: The recently awarded planning grant from the Safe Streets For All program provides funding for this task. The grant agreement with USDOT/FHWA has been executed and work is underway; staff anticipates regular check-ins with the BCC and Town Council as we gather public input on desired context sensitive design solutions throughout the Town and County. Timing for any specific Town and County LDR amendments are TBD.
Progress | 20% FY23-FY24 County Public Works |  |  | 
Timeframe |  |  |  | 
Task Lead |  |  |  | 
Resources | FY23 | FY24 | FY25 | Total
Long Range Planning | 20 hrs. | 0 hrs. | 80 hrs. | 100 hrs.
County Planning Director | 3 hrs. | 7 hrs. | 7 | 10 hrs.
County Public Works - Pathways, Engineering, Road and Levee | 50 hrs. | 20 hrs. | 180 | 250 hrs.
FY 25+

## Slide 19
Wildlife Crossings Master Plan Implementation
ITP Action Items: Chapter 5- Major Capital Projects: Wildlife Protection
Task: Developing safe wildlife crossings benefits wildlife and human safety and welfare. The Wildlife Crossings Master Plan was completed in May 2018. Implementing its recommendations will be an ongoing project over the next 5-10 years.
Status: Wildlife Crossings Master Plan has been completed. Implementation is in initial stages with SPET funding approved. County Public Works completed 30% design plans for the three road segments (US HWY 26/89/191 – Camp Creek area, North US HWY 89/191 – between the USFWS Fish Hatchery and Town of Jackson, and Wyoming Highway 22 – West side of Teton Pass). Our plan is to move each of these project areas on their own individual timelines as we identify and secure construction funding through various state and federal funding opportunities. We also will be spending funds on the Teton County portion of Highway 22/390 intersection – Snake River bridge replacement including two county funded underpasses and fence treatments. All of these projects are in cooperation with public land agencies, WYDOT, and WGFD.
Progress | 30% Ongoing – 2030 County Public Works |  |  |  | 
Timeframe |  |  |  |  | 
Task Lead |  |  |  |  | 
Resources | FY 22 | FY23 | FY 24 | FY 25 | Total
County Pro. Services | $668,329 | $432,851 | $1,491,707 | $5,750,000 | $8,342,887
Town Pro. Services | TBD | TBD | TBD | TBD | TBD
County Planning Director | Ongoing | 0 hrs | 0 hrs | 0 hrs | Ongoing
Town Planning Director | Ongoing | 0 hrs | 0 hrs | 0 hrs | Ongoing
County Engineering | Ongoing | Ongoing | 600 hrs | 800 hrs | Ongoing
FY 24-25

## Slide 20
Town Workforce Housing Mitigation LDRs
Comp Plan Strategies:
5.3.5.2: Update current mitigation requirements as necessary.
Task: Town will work to revisit the current structure, rates and exemptions for workforce housing mitigation required by the LDRs. This effort will be separate yet concurrent with the similar County Update that will need to be coordinated between the two jurisdictions.
Status: A contract amendment was approved during the March 6, 2023 Joint Information Meeting. Policy work with a stakeholder group began in February of 2023 and final policy discussion went before a joint policy workshop in summer of 2023. Draft LDRs have been prepared by Staff, however the public release has not yet occurred. The project is currently on hold per Town Council and County Commission direction.
Progress | 80% December 2022- TBD Long-Range Planning & Housing Department | 
Timeframe |  | 
Task Lead |  | 
Resources | FY 23-24 | Total
Consulting Services (Town) | $76,500.00 | $76,500.00
Housing Director | 20 hrs | 20 hrs
Housing Department | 20 hrs | 20 hrs
Long Range Planning | 100 hrs | 100 hrs
Town Planning Director | 80 hrs | 80 hrs
County Planning | 0 hrs | 0 hrs
FY 24-25

## Slide 21
County Workforce Housing Mitigation LDRs
Comp Plan Strategies:
5.3.5.2: Update current mitigation requirements as necessary.
Task: The County will work to revisit the current structure and rates for workforce housing mitigation required by the LDRs.
Status: A contract amendment was approved during the March 6, 2023 Joint Information Meeting. Policy work with a stakeholder group began in February of 2023 and final policy discussion went before a joint policy workshop in summer of 2023. Draft LDRs have been prepared by Staff, however the public release has not yet occurred. The project is currently on hold per Town Council and County Commission direction. .
Progress | 80% December 2022- TBD County Long-Range Planning & Housing Department | 
Timeframe |  | 
Task Lead |  | 
Resources | FY 23-24 | Total
Consulting Services (County) | $76,500 | $76,500
Housing Director | 20 hrs | 20 hrs
Housing Department | 80 hrs | 80 hrs
Long Range Planning | 200 hrs | 200 hrs
County Planning Director | 20 hrs | 20 hrs
County Planning | 20 hrs | 20 hrs
FY 24-25

## Slide 22
Town Karns Meadow Master Plan Implementation
Comp Plan Strategies:
3.2.S.1: Update zoning and land development regulations within Complete Neighborhoods to achieve the desired character for Complete Neighborhoods as established in Character Districts
3.2.S.2: Identify locations for locally-oriented and visitor-oriented nonresidential uses within Complete Neighborhoods based on the Character Districts.
3.2.S.3: Update land development regulations for nonresidential areas within Complete Neighborhoods to encourage ground floor vitality and flexible mixed use
3.2.S.5: Evaluate and update regulations in Complete Neighborhoods to allow and promote the appropriate variety of housing types identified through the Character Districts.
3.2.S.6: Evaluate and update design regulations to encourage quality public space.
Task: Planning and development of Karns Meadow Park, including completion of a Master Plan describing all desired improvements followed by the approval of individual or combined conditional use permits for each component of the property. Development will provide activation of the park through outcomes identified in the planning process.
Status:. This project is underway. In 2018, Council authorized the Parks and Recreation Department to complete a comprehensive environmental assessment of the property. The assessment recommended the completion of a ‘current condition’s active management plan,’ and sequentially, the completion of the site master plan. The management plan was completed in 2019. In the summer and fall of 2022, staff started the process of developing the site master plan. Community engagement sessions and a survey were completed in March of 2023, and rezoning of the tracts was finalized that fall. The team currently awaits the completion of the alternatives analysis and will begin the conditional use permit process in the Spring/Summer of 2024. Phase one development will follow in 2025.
Progress | 60% FY23 & FY24 Parks and Recreation & Ecosystem Stewardship Administrator |  |  | 
Timeframe |  |  |  | 
Task Lead (s) |  |  |  | 
Resources | FY23 | FY24 | FY25 | Total
Ecosystem Stewardship Position | 150 hrs | 200 hrs | 200 hrs | 550 hrs
Town Planning | 50 hrs | 50 hrs | 100 hrs | 200 hrs
Parks and Recreation | 200 hrs | 400 hrs | 400 hrs | 600 hrs
FY 24-25+

## Slide 23
Town Climate Action Plan
Comp Plan Strategies:
2.G.S.2 Develop an Emissions Reduction and Climate Action Plan to identify potential solutions and strategies to reduce our contribution to climate change and better position the Town and County to be able to deal with potential impacts of a changing climate. The Plan should outline implementation responsibilities and include adaptation measures specific to the potential impacts of climate change on our economy.
Task: Town staff continues to work with the Jackson Hole Climate Action Collective (JHCAC) and Teton Climate Action Partnership (TCAP) by providing staff time to assist with project information, facilitation, or leadership in order to help with climate action and equity projects. Town staff is building upon the work of these groups to draft a Town Sustainability Plan.
Status: The Town of Jackson hired an Ecosystem Stewardship Administrator (ESA) in May of 2022. 20% of their time is allocated to helping TCAP and JHCAC with their efforts. Another 20% is allocated to the Town Sustainability Plan. The ESA and other Town staff attend quarterly coordinating meetings, assist TCAP and JHCAC with identification of funding opportunities, and serve as liaisons between the groups and the Town. The ESA is currently working with both groups to build their work into the Town of Jackson Sustainability Plan. Sustainability Plan priorities and strategies were presented to Council in December of 2023, and a final draft will be presented for approval in June of 2024. If approved, implementation of the Sustainability Plan will follow.
Progress | 75% July 2021-June 2024 Ecosystem Stewardship Administrator |  |  |  | 
Timeframe |  |  |  |  | 
Task Lead |  |  |  |  | 
Resources | FY 22 | FY 23 | FY24 | FY25 | Total
Other Town Staff | 100 hrs | 100 hrs | 50 hrs | 0 hrs | 250 hrs
Ecosystem Stewardship | 0 hrs | 250 hrs | 800 hrs | 20 hrs | 1070 hrs
Long-Range Planning | 20 hrs | 0 hrs | 0 hrs | 0 hrs | 20 hrs
FY 24-25+

## Slide 24
Town Climate Implementation
Comp Plan Strategies:
2.G.S.2 Develop an Emissions Reduction and Climate Action Plan to identify potential solutions and strategies to reduce our contribution to climate change and better position the Town and County to be able to deal with potential impacts of a changing climate. The Plan should outline implementation responsibilities and include adaptation measures specific to the potential impacts of climate change on our economy.
Task: Town staff will map out a detailed timeline for implementation of climate action strategies within the Town Sustainability Plan and begin implementation. Town staff will also continue to work with the Jackson Hole Climate Action Collective (JHCAC) and Teton Climate Action Partnership (TCAP) to support community-wide climate action projects, identify potential funding opportunities, and serve as a liaison between those groups and the Town.
Status: Upon approval of the Town Sustainability Plan, which is scheduled for review by the Town Council in June of 2024, Town staff will begin implementation of strategies within the plan. Each strategy within the plan has a corresponding timeline of completion by 2026, 2028, 2030, or 2035. While a few strategies need more than a decade to complete, most strategies will be completed by 2030, and staff should plan on drafting an updated plan at that time. Some strategies are already on the Council agenda for 2024.
Progress | 0% July 2024-June 2030 Ecosystem Stewardship Administrator | 
Timeframe |  | 
Task Lead |  | 
Resources | FY25 | Total
Other Town Staff | 100 hrs | 100 hrs
Ecosystem Stewardship | 400 hrs | 700+ hrs (20% of Ecosystem Administrator)
Long-Range Planning | 20 hrs | 20 hrs
FY 24-25+

## Slide 25
Highway 22 Capital Multi-Modal Transportation Projects
ITP Action Items: Chapter 5- Major Capital Projects
Task:.
  Highway 22 Jackson to Wilson Corridor Study, i.e. the Hwy22 NEPA study.
    Status: WYDOT is project lead and has moved up the planning in their STIP to WYDOT’s FY2023. This project is underway and WYDOT held a public meeting on February 22, 2024 https://wy22corridor.com/.
  WY22 Pathway, Wilson to Stilson.
    Status: This project has been completed.
Progress | Varies Varies County Public Works | 
Timeframe |  | 
Task Lead |  | 
Resources | FY25 | Total
Long Range Planning | 0 hrs | 0 hrs
County Planning Director | 0 hrs | 0 hrs
Town Com. Dev. Director | 0 hrs | 0 hrs
County Public Works | 400 hrs | 400 hrs
Regional Transportation Planning Administrator | 200 hrs | 200 hrs
FY 24-25+

## Slide 26
Develop Comp Plan Indicators for Chapter 1 (Ecosystem Stewardship)
Comp Plan Strategies:
1.G.S.1: Identify appropriate indicators that measure achievement of the Chapter goal. For example, measuring stewardship of natural resources may include establishing indicators for percent change of site development within the Town and County, or tracking contaminant loading from wastewater discharge at the Town of Jackson treatment facility.
1.G.S.2: Establish an Ecosystem Stewardship target for an Adaptive Management Program that will be used to track the Town and County’s progress toward goals related to this chapter.
Task: The Town and County jointly use the annual Indicator Report and Adaptive Management Program to evaluate progress in achieving the Comp Plan goals, but measurable and meaningful indicators for ecosystem stewardship need to be evaluated.
Status: The Ecosystem Stewardship Administrator has begun this work for the Town by 1) looking at indicators used by other communities, and 2) gathering stakeholder groups to discuss what data is being collected, where there are gaps in current data collection, and 3) which data sets provide the best indicators of ecosystem health. Stakeholder meetings were completed in winter and spring of 2023. Staff presented recommendations for the Town in December of 2023 for an ecosystem health indicator report.
Progress | 20% FY23 & FY24 Ecosystem Stewardship Administrator |  |  | 
Timeframe |  |  |  | 
Task Lead |  |  |  | 
Resources | FY23 | FY24 | FY25 | Total
Ecosystem Stewardship | 200 hrs | 200 hrs | 400 hrs (including summer intern) | 800 hrs
Long Range Planning | 10 hrs | 0 hrs | 0 hrs | 20 hrs
Town Manager | 20 hrs | 10 hrs | 10 hrs | 40 hrs
FY 24-25+

## Slide 27
Town Water Quality Initiatives
Comp Plan Strategies:
1.2.S.1: Evaluate and update natural resource protection standards for waterbodies, wetlands and riparian areas.
1.2.S.2: Evaluate and update surface water filtration standards, focusing on developed areas near important waterbodies.
Task: A clear priority of the 2020 Comprehensive Plan update was the need to maintain and enhance water quality, which is essential to both ecosystem and human health. This task includes three action components:
Wastewater Treatment Facility Study (WQMP) (support County)
Stormwater Management Program (Town)
Wastewater Treatment Plant (WWTP) Upgrade Planning (Town)
Status:.
The WQMP is complete and Town staff will work with County staff to implement action items related to the Town that Council chooses to pursue.
The Town’s Stormwater Management Program is in development with the hired consultant team. The FY24-FY25 effort will result in new LDR content and completing the comprehensive Stormwater Management Program document addressing multiple pollution sources.
Town staff anticipates receiving an updated discharge permit from the State. Any new water quality requirements, along with data analysis of existing post-discharge wetlands treatment and Council-adopted WQMP action items related to the WWTP, will help identify alternatives for capital improvements. Staff will present policy questions and recommendations to Town Council, likely in summer 2024.
Progress | 70% December 2021-January 2025 Town Public Works |  |  |  |  | 
Timeframe |  |  |  |  |  | 
Task Lead |  |  |  |  |  | 
Resources | FY 21 | FY 22 | FY 23 | FY24 | FY25 | Total
Long-Range Planning | 0 hrs | 10 hrs | 0 hrs | 0 hrs | 5 hrs | 15 hrs
Town Public Works | 0 hrs | 100 hrs | 285 hrs | 220 hrs | 300 hrs | 905 hrs
Ecosystem Stewardship | 0 hrs | 0 hrs | 100 hrs | 80 hrs | 20 hrs | 200 hrs
Town Planning Director | 0 hrs | 10 hrs | 20 hrs | 10 hrs | 25 hrs | 65 hrs
FY 25+

## Slide 28
ITP Transportation Demand Management/Emerging Mobility Plan
ITP Action Items: Chapter 4, Transportation Demand Management: Establish a TDM Program.
Task: ITP Chapter 4 discussed potential Travel Demand Management strategies. Many technology-enabled opportunities, or partnership and data sharing opportunities were not discussed in the ITP. These could include incentives for businesses or non-profit sectors to more seamlessly connect with existing transportation options. Mobility Hubs can also support more active transportation modes.
Status: Staff will present findings from this study at the May 2024 JIM. Transportation Staff included carrying out adopted recommendations from the 2019 Downtown Parking study in the Transportation Workplan (3/4/2024 MJM)
Progress | 10%
Timeframe | To be determined
Task Lead | Regional Transportation Planning Administrator
Resources | 200 hours; $225,000 requested in FY24 budget
FY 25+
Notes: Prior task description: Complete the 2016 Parking Study Charter by studying regional park ‘n ride needs. Develop and implement a Transportation Demand Management program to help achieve the community goal meeting future transportation demand with alternative modes. TDM strategies will complement START operations and will manage performance monitoring and reporting system. Upon completion of the regional park ‘n ride study it should be considered along with the Town downtown (including paid parking) and residential parking studies to coordinate next steps and implementation.

## Slide 29
Large Building and Workforce Housing Bonus Review
Comp Plan Strategies:
Policy 3.3.c Provide predictability in land use decisions
Policy 4.1.b Emphasize a variety of housing types, including deed-restricted housing
Policy 4.1.c Promote compatible infill and redevelopment that fits Jackson neighborhoods
Policy 5.4.d Provide incentives for the provision of workforce housing
Task: This task will look at the Town various LDRs and recent LDR changes that have incentivized or facilitated the development of large buildings in the Town. In particular, changes to the LDRs regarding maximum building size, workforce housing bonuses (2:1 bonus and 4th-story bonus), development review thresholds, and the trend of landowners aggregating larger sites, have contributed to creating larger projects in recent years, especially for multi-family development. The intent for this project is to reevaluate some or all of these tools to see if changes are necessary to better balance community character concerns, the need for true workforce housing, and the market limitations of private developers to construct workforce housing at a scale that make financial sense.
Status:. TBD. This project started with a workshop in November and Planning Commission review in December 2023. This project is currently not in FY 25 workplan.
Progress | 10% October 2023-June 2024 Town Planning | 
Timeframe |  | 
Task Lead |  | 
Resources | FY24 | Total
Consultant Resources | $20,000.00 | $20,000.00
Town Planning Director | 100 hrs | 100 hrs
Town Senior Planner | 20 hrs | 20 hrs
Joint Long Range Associate Planner | 10 hrs | 10 hrs
FY 24-25+

## Slide 30
County Review of Accessory Residential Units in Nonresidential Zones
Comp Plan Strategies:
Policy 3.3.b: Provide predictability in land use decisions – Updating these regulations may increase predictability by all including landowners wishing to complete infill development, and neighbors to said development so that folks can generally expect what to see as the result of additional infill being constructed.
Policy 5.2.c: Provide workforce housing solutions locally Our primary housing goal is to limit the percentage of the local workforce commuting from other counties. Therefore, required workforce housing mitigation and public investments in workforce housing will be located within our community. However, achievement of our housing goal could still mean that a large portion of our workforce will reside outside of the community and commute into the Town or County. The community will continue to pursue efforts to limit the impacts of commuters on the ecosystem and neighboring communities.
Policy 5.4.b: Avoid regulatory barriers to the provision of workforce housing The Town and County will avoid regulatory barriers that inadvertently preclude workforce housing in a manner that is consistent with the community’s Common Values. This may include providing exemptions from certain requirements for developments that provide new subsidized workforce housing that reduces the shortage of housing that is affordable to the local workforce.
Task: Review the County LDRs for nonresidential Accessory Residential Units (ARUs) to determine if the regulations are achieving the desired outcome, including review of the required permitting process. Consider policies to facilitate and streamline the creation of deed-restricted ARUs in nonresidential zones that support local businesses while ensuring an appropriate level of review, notice, and public comment.
Status: This item was suggested by the Board in March 2023 for consideration of inclusion in the Work Plan.
Progress | 5% July 2023 – December 2023 County Long Range Planning |  | 
Timeframe |  |  | 
Task Lead |  |  | 
Resources | FY 23 | FY 24 | Total
County Planning Director | 20 hrs | 40 hrs | 60 hrs
Long-Range Planning | 5 hrs | 120 hrs | 125 hrs
County Planning | 5 hrs | 20 hrs | 25 hrs
FY 24-25+

## Slide 31
County Safe Streets & Roads for All
Comp Plan Strategies:
7.2.S.1: Develop a Countywide Integrated Transportation Plan
7.2.S.5: Discuss with neighboring jurisdictions and State and Federal officials the costs and benefits of funding sources and planning options, such as a Regional Transportation Authority.
7.3.S.2: Consider specific provisions for current planning review to require alternative transportation components in new development.
Task: Utilizing the Town Community Streets Plan for guidance, the County will work with road, pathway, and utility designers to update the County road, utility, and easement standards.
Status: Transportation Engineering Design Standards (TEDS) is a deliverable from the Safe Streets for All (SS4A) work, anticipated to be complete by December 2025. The standards would then move through the adoption process
FY 24-25+
Progress | 2% Federal Grant (February 2024-Winter 2025) County Public Works |  | 
Timeframe |  |  | 
Task Lead |  |  | 
Resources | FY24 | FY 25 | Total
Long Range Planning | 0 hrs | 4 hrs | 4hrs
County Planning Director | 0 hrs | 2 hrs | 2 hrs
Town Planning Director | 0 hrs | 2 hrs | 2 hrs
Pathways Coordinator | 400 hrs | 100 hrs | 500 hrs
Regional Transportation Planning Administrator | 200 hrs | 125hrs | 325 hrs

## Slide 32
FY 24-25
Town Hillside LDRs
Comp Plan Strategies:
3.4.S.1: Study and map avalanche and landslide areas.
3.4.S.3: Evaluate and update development regulations for naturally hazardous areas based on mapping.
Task: Update Town hillside regulations to incorporate improved landside, rockfall, liquefaction, seismic, and avalanche hazard information and implement best practices for identifying, avoiding, and mitigating risks of development in hazardous areas. The County may ultimately adopt those portions relevant in the County but may do so through a later, separate process once the Town has refined the standards through its adoption process.
Status: Originally identified in the FY16 Work Plan as a subtask of a greater set of miscellaneous amendments; begun in June 2017 but put on hold because of the prioritization of the Engage 2017 projects; taken up again following the conclusion of the Engage 2017 projects. The consultant group has provided draft hillside development regulations and a hazard map for consideration. The drafts provided were not consistent with the format or processes already formalized by existing Town regulations, so staff has spent significant time adjusting and editing these documents before public release and review. This project has been put on hold and was not added during the January 2024 Town Council retreat as a priority to continue.
Progress | 80% July 2018- August 2024 Town Planning |  |  |  |  |  |  | 
Timeframe |  |  |  |  |  |  |  | 
Task Lead |  |  |  |  |  |  |  | 
Resources | FY 18 | FY 19 | FY20 | FY 21 | FY 22 | FY 23 | FY 24 | Total
Consulting Services (Town) | $ 0 | $ 0 | $31,269 | $1,970 | $0 | $0 | $0 | $33,239
Long-Range Planning | 40 hrs | 110 hrs | 70 hrs | 50 hrs | 50 hrs | 10 hrs | 5 hrs | 335 hrs
Town Com. Dev. Director | 0 hrs | 20 hrs | 20 hrs | 20 hrs | 10 hrs | 5 hrs | 5 hrs | 75 hrs
Town Engineer | 0 hrs | 20 hrs | 20 hrs | 40 hrs | 40 hrs | 30 hrs | 30 hrs | 180 hrs
Town Planning Director | 0 hrs | 20 hrs | 20 hrs | 40 hrs | 40 hrs | 15 hrs | 15 hrs | 150 hrs
Town Planning | 0 hrs | 20 hrs | 0 hrs | 0 hrs | 30 hrs | 40 hrs | 40 hrs | 130 hrs

## Slide 33: New Fiscal Year 25 Tasks
The following tasks have not yet begun, and prioritization of timeline, staff, and fiscal resources is needed. This section is the primary focus of setting the FY 25 Work Plan and will add new tasks to the current project workload.

## Slide 34: New Fiscal Year 25+ Tasks
Project | Estimated Timeframe | Page Number
County Business Park | FY 2025-2026 | 36
County Water Quality LDRs | July 2024-June 2025 | 37
Traffic Impact Study LDRs | FY 2025 | 38
Teton County Fire Protection Resolution for New Subdivisions - LDR Amendment | FY 2025 | 39
County Aspens Commercial Zoning Update | FY25 & FY26+ | 40

## Slide 35
County Business Park Zoning
Comp Plan Strategies:
3.2.S.1: Update zoning and land development regulations within Complete Neighborhoods to achieve the desired character for Complete Neighborhoods as established in Character Districts
3.2.S.2: Identify locations for locally-oriented and visitor-oriented nonresidential uses within Complete Neighborhoods based on the Character Districts.
3.2.S.3: Update land development regulations for nonresidential areas within Complete Neighborhoods to encourage ground floor vitality and flexible mixed use.
3.2.S.5: Evaluate and update regulations in Complete Neighborhoods to allow and promote the appropriate variety of housing types identified through the Character Districts.
3.2.S.6: Evaluate and update design regulations to encourage quality public space.
6.2.S.3: Maintain locations for light industry, and evaluate and update regulations relating to live-work light industry opportunities.
6.3.S.2: Evaluate and update land use regulations to foster a positive atmosphere and attract appropriate types of business to the community. Promote the types of uses that provide middle income jobs and promote entrepreneurship.
Task: Update zoning allowing light industrial uses. This area specifically includes South Park Business Park (Subarea 7.1).
Status: This Task has not begun.
Progress | 0% FY2025-2026 Joint Long-Range Planning
Timeframe | 
Task Lead | 
Resources | To be determined
FY 25+

## Slide 36
County Water Quality LDRs
Comp Plan Strategies:
1.2.S.1: Evaluate and update natural resource protection standards for waterbodies, wetlands (including jurisdictional and non-jurisdictional) and riparian areas.
1.2.S.2: Evaluate and update surface water filtration standards, focusing on developed areas near significant
1.2.S.5: Investigate updates to the Land Development Regulations and other County resolutions and Town ordinances to provide further protection for Public Water Systems, surface water, and groundwater, including, incentives for wastewater system best management practices, facility regulations, monitoring wells, and buffering distances.
1.2.S.6: Enhance existing water quality protection tools and explore the development of new tools such as an aquifer protection overlay or a water quality commission.
Task: Utilizing the completed Water Quality Master Plan (scheduled to be complete May 2024), begin the process of updating the water quality LDRs, specifically focusing on protection standards, water filtration standards, management of wastewater, surface water and groundwater, and implementing tools to protect drinking water.
Status: This task will begin when the Water Quality Master Plan is complete and adopted by the County Commission. The consultant Trihydro has made recommendations on future water quality LDRs, including the adoption of surface water and aquifer protection overlays.
Progress | 0% After completion of County Water Quality Master Planning Long-Range Planning
Timeframe | 
Task Lead | 
Resources | To be determined
FY 25

## Slide 37
Traffic Impact Study LDRs
Task: Currently there are no standards related to implementation of traffic mitigation for large development projects. In many jurisdictions, standards exist which inform the development community on how to complete a Traffic Impact Study, what standards are necessary for a complete report, and baseline information related to any mitigation measures necessary for a particular project. The Regional Transportation Planning Administrator has completed a draft guideline document for Traffic Impact Studies. In order for these guidelines to be utilized as requirements for large projects, Staff is requesting that these become a part of the Land Development Regulations.
Status: A draft of the guidelines have been completed, however work to include these within the LDRs has not yet begun.
Progress | 0% July 2024 - June 2025 Long-Range Planning & Regional Transportation Planning Administrator (Joint Town & County Effort) | 
Timeframe |  | 
Task Lead |  | 
Resources | FY 24-25 | Total
Consulting Services | $TBD | $TBD
Long Range Planning | 100 hrs | 100 hrs
Town Planning Director | 20 hrs | 20 hrs
County Planning Director | 20 hrs | 20 hrs
Regional Transportation Planning Administrator | 100 hrs | 100 hrs
FY 25+
Comp Plan Principle:
Principle 8.2 Coordinate provision of infrastructure and facilities needed for service delivery.

## Slide 38
Teton County Fire Protection Resolution for New Subdivisions - LDR Amendment
Comp Plan Strategies:
3.4.f Protect development against wildfire. Surrounded by National Forest lands, private lands throughout the community are susceptible to wildfires. The mapped Wildland Urban Interface will continue to be updated and refined, and development in such areas will continue to mitigate for wildfire hazard.
Task: Currently Teton County has adopted a resolution for fire protection standards related to new subdivisions. This has created some confusion as these standards are not adopted as rules within the County Land Development Regulations. Staff recommends adding this workplan item in order to adopt the similar standards as regulations within the LDRs this next fiscal year and removing the “Teton County Fire Protection Resolution For New Subdivisions” (2021).
Status:. This project has not yet begun.
Progress | 0% FY25 County Planning (Current Planning) | 
Timeframe |  | 
Task Lead (s) |  | 
Resources | FY25 | Total
County Planning | 100 hrs | 100 hrs
County Planning Director | 20 hrs | 20 hrs
County Attorney’s Office | 5 hrs | 5 hrs
FY 25

## Slide 39
County Aspens Commercial Zoning Update
Comp Plan Strategies:
3.2.S.1: Update zoning and land development regulations within Complete Neighborhoods to achieve the desired character for Complete Neighborhoods as established in Character Districts
3.2.S.2: Identify locations for locally-oriented and visitor-oriented nonresidential uses within Complete Neighborhoods based on the Character Districts.
3.2.S.3: Update land development regulations for nonresidential areas within Complete Neighborhoods to encourage ground floor vitality and flexible mixed use
3.2.S.5: Evaluate and update regulations in Complete Neighborhoods to allow and promote the appropriate variety of housing types identified through the Character Districts.
3.2.S.6: Evaluate and update design regulations to encourage quality public space.
Task: Second phase of the Aspens Character District zoning update to implement the 2020 Comprehensive Plan. This portion of the Aspens update is expected to be more time consuming than the first phase as there are several PUDs and commercial properties to examine (Aspens commercial and residential areas, Teton Pines). The County will create new County zones and clean up Master Plans for these Subareas that balance the existing character of the multi-family and commercial development with the goals outlined in the Comprehensive Plan. Due to the complexities of the existing regulations and plans in place, the need for outreach and facilitation with an engaged neighborhood, and the potential transformational nature of this project it is expected to be a similar timeframe and budget to the Northern South Park neighborhood planning process.
Status: This task has not yet begun. Staff has anticipated that this task will begin once Northern South Park Implementation and Natural Resource LDRs have been completed.
Progress | 0% | 
Timeframe | TBD | 
Task Lead | County Long-Range Planning | 
Resources | FY24+ | Total
Consulting Services (County) | TBD | TBD
Long-Range Planning | 800 hrs | 800 hrs
County Planning Director | 90 hrs | 90 hrs
County Planning | 20 hrs | 20 hrs
FY 25+

## Slide 40: Ongoing Tasks
The following tasks are projects completed annually or on an ongoing basis. Resource allocation to these tasks may be seasonal, as in the case of Indicator Report preparation, or LDR or Zoning Map Amendment applications made by the public. No prioritization of these tasks is needed unless there is interest to remove or add continuous or regular tasks.

## Slide 41: Ongoing Tasks
Project | Page
Joint Annual Indicator Report | 43
Joint Annual Work Plan | 44
Teton County Scenic Preserve Trust | 45
County Biennial LDR Cleanups | 46
Town Biennial LDR Cleanups | 47
County LDR and Zoning Map Amendments | 48
Town LDR and Zoning Map Amendments | 49
LDR and Comp Plan Education and Outreach | 50
Data Requests | 51
Other Comp Plan Coordination | 52

## Slide 42
Ongoing Tasks
Joint Annual Indicator Report
Comp Plan Strategies:
Policy 9.2.a: Monitor indicators annually
Task: Compile and publish annual indicator data. Analyze indicator data and execution of the past year’s Implementation Work Plan to inform an Implementation Work Plan for the following year. Constantly monitor community trends and understand how to best achieve the vision of the Comprehensive Plan. Additional hours may be necessary for next year’s Indicator Report since the GMP/Comp Plan Update and Data Standardization are underway and will require adjustments to the Indicator Report.
Status: This task occurs annually and is a part of every year’s work plan.
Progress | Annual December-April Long-Range Planning
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 200 hrs
County Planning Director | 5 hrs
Town Planning Director | 20 hrs
Housing Department | 5 hrs

## Slide 43
Joint Annual Work Plan
Comp Plan Strategies:
Policy 9.2.b: Establish an implementation work plan annually
Task: Analyze indicator data and execution of the past year’s Implementation Work Plan to establish an Implementation Work Plan for the upcoming year.
Status: This task occurs annually and is a part of every year’s work plan.
Progress | Annual December – April Long-Range Planning
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 100 hrs
County Planning Director | 10 hrs
Town Planning Director | 10 hrs
Housing Department | 5 hrs
Ongoing Tasks

## Slide 44
Teton County Scenic Preserve Trust
Comp Plan Strategies:
1.4.S.4 – Explore establishment of a dedicated funding source for the acquisition of permanent open space for wildlife habitat protection, scenic vista protection, and agriculture preservation.
1.4.S.6 – Reevaluate the purpose and staffing of the Teton County Scenic Preserve Trust to provide full-time management for the organization and consider the adoption of higher operational standards.
Task: Administer the Teton County Scenic Preserve Trust easement. This includes working with a consultant (including contract maintenance and tracking) to monitor the program, determining if violations exist, and facilitating enforcement resolution process with landowners. Staff also facilitates any new easements or amendments to existing easements through the hearing process.
Status: This is an ongoing annual task. Beginning in late 2023 & early 2024 staff worked on a new contract with a new vendor, and amendments to the monitoring process which has included additional time for outreach related to each easement by staff, additional time for enforcement issues, and submittal of reports to each easement holder.
Progress | Annual Spring-Fall Long-Range Planning
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 250 hrs (increased from prior years by 100 hours)
County Planning | 10 hrs
County Planning Director | 10 hrs
Consultant Services | $19,595 (for FY23—varies annually)
Ongoing Tasks

## Slide 45
County LDR Maintenance
Comp Plan Strategies:
3.3.S.2: Evaluate and update base allowances to predictably allow development that is consistent with our Vision.
3.3.S.3: Evaluate and update incentives so that they are performance based, tied to measurable community benefits, limited, and more consistent with base allowances.
Task: Revisit LDR updates that have been made in the recent past to cleanup errors and address unintended consequences. Ensure the LDRs are kept current, unlike the period from 1994-2015 when they were largely unattended and became unmanageable. Major unintended consequences that merit more specific review will be addressed as separate tasks. Other annual updates that are required by the LDRs include the housing fee in lieu rate and exaction fee rate.
Status: The County went through its latest cleanup in January of 2023.
Progress | Biennial July-December County Long-Range Planning
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 80 hrs
County Planning Director | 5 hrs
County Planning | 15 hrs
Ongoing Tasks

## Slide 46
Town LDR Maintenance
Comp Plan Strategies:
3.3.S.2: Evaluate and update base allowances to predictably allow development that is consistent with our Vision.
3.3.S.3: Evaluate and update incentives so that they are performance based, tied to measurable community benefits, limited, and more consistent with base allowances.
Task: Revisit LDR updates that have been made in the recent past to cleanup errors and address unintended consequences. Ensure the LDRs are kept current, unlike the period from 1994-2015 when they were largely unattended and became unmanageable. Major unintended consequences that merit more specific review will be addressed as separate tasks. Other annual updates that are required by the LDRs include the housing fee in lieu rate and exaction fee rate.
Status: The Town of Jackson Planning Department completed one LDR cleanup in January 2019. A second, and more comprehensive, cleanup is needed to keep the Town LDRs updated. These cleanups should occur annually in the second half of the year to keep the LDRs up to date in incorporate any Planning Director interpretations or changes to State law. The Town Attorney’s office has identified the following changes resulting from the 2021 Wyoming Legislative season that may require updates to the LDRs:
HB79: relates to State-exempt land subdivisions for gift to family
HB157: terms of connection to municipal infrastructure
HB158: relationship between zoning, land use plans (Comp Plan) and land use decisions
Progress | Biennial December - July Town Planning
Timeframe | 
Task Lead | 
Resources | 
Town Planning Director | 100 hrs
Town Planning | 25 hrs
Consultant Services | $10,000 - $14,000
Ongoing Tasks

## Slide 47
County LDR and Zoning Map Amendments
Comp Plan Strategies: variable depending on the amendment proposed by the public, other department, or elected officials.
Task: Acknowledge the time and resources required for the various day-to-day tasks for which staff is responsible. For the Long Range Planning Team, this includes LDR and zoning map amendments. These are projects that are proposed by the public or other departments that are not otherwise a part of this work plan, and in recent years have required significant staff, public, and elected official resources. For this task, it should be noted that the time estimates provided in the chart represent the typical amount of time available to spend on these projects, but that the resources required are variable depending on the number and complexity of applications submitted by the public or requested by other departments and elected officials. Projects under this task may be recategorized as separate projects in this work plan if they represent a greater priority.
Status: This is an ongoing task that is a part of every year’s Work Plan.
Progress | Ongoing As Requested Various
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 600 hrs
County Planning Director | 60 hrs
Housing Department | 20 hrs
List of Projects completed in FY 24:
Outdoor Reception LDR Text Amendment
Moulton Family Inholding Zoning
Environmental LDR Amendments
Ongoing Tasks

## Slide 48
Town LDR and Zoning Map Amendments
Comp Plan Strategies: variable depending on the amendment proposed by the public, other department, or elected officials.
Task: Acknowledge the time and resources required for the various day-to-day tasks for which staff is responsible. For the Long Range Planning Team, this includes LDR and zoning map amendments. These are projects that are proposed by the public or other departments that are not otherwise a part of this work plan, and in recent years have required significant staff, public, and elected official resources. For this task, it should be noted that the time estimates provided in the chart represent the typical amount of time available to spend on these projects, but that the resources required are variable depending on the number and complexity of applications submitted by the public or requested by other departments and elected officials. Projects under this task may be recategorized as separate projects in this work plan if they represent a greater priority.
Status: This is an ongoing task that is a part of every year’s Work Plan.
Progress | Ongoing As Requested Various
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 10 hrs
Town Planning Director | 50 hrs
Town Planning | 150 hrs
Housing Department | 10 hrs
Ongoing Tasks
Applications submitted in FY23/24
P23-015: PUD Amendment for Snake River Canyon Ranch (Teton County).
P23-016: text amendment to increase bike parking requirements by County Pathways Dept.
P23-079: Map amendment for Karns Meadow by Parks and Rec Dept.
P23-204: Amendment to PUD Master Plan for Cottonwood Park by Presbyterian Church of Jackson Hole.

## Slide 49
LDR and Comp Plan Education and Outreach
Comp Plan Strategies:
3.3.S.1: Consider a joint Town and County staff person to execute the Growth Management Program and otherwise implement the Comprehensive Plan.
Task: Ensure the public is engaged in the implementation of the Comp Plan. Coordinate the public engagement requirements of the tasks in this Work Plan. Communicate the community vision, where it came from, and how it is being achieved. This task includes regularly updating the Long-Range Planning website, emailing subscribers to planning updates, coordinating with other departments and local or regional agencies, and providing funding and staffing to public workshops, charrettes and stakeholder meetings.
Status: This is an ongoing task that evolves with different projects.
Progress | Ongoing Ongoing Long-Range Planning
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 80 hrs
County Planning Director | 20 hrs
County Planning | 20 hrs
Town Planning Director | 40 hrs
Town Planning | 20 hrs
Ongoing Tasks

## Slide 50
Data Requests
Comp Plan Strategies:
Policy 8.1.a: Maintain current, coordinated plans for delivery of desired service levels.
Task: As government and non-government organizations plan for service delivery, Long-Range Planning staff can provide consistent data and projections on the population and demographics of the community, limiting consultant fees and standardizing level of service planning across the community.
Status: This task occurs annually and is a part of every year’s work plan.
Progress | Ongoing As Requested Long-Range Planning
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 50 hrs
Ongoing Tasks

## Slide 51
Other Comp Plan Coordination
Comp Plan Strategies:
Varies
Task: In addition to the specific tasks described above, Long-Range Planning will assist other departments and agencies to coordinate consistency with the Comp Plan.
Status: This task occurs annually and is a part of every year’s work plan.
Progress | Ongoing Ongoing Long-Range Planning
Timeframe | 
Task Lead | 
Resources | 
Long-Range Planning | 100 hrs
County Planning Director | 75 hrs
Ongoing Tasks

## Slide 52: Future Tasks – Non-Budgeted and/or Unscheduled
The following tasks are in the line-up for implementation in future years but are not recommended to begin in Fiscal Year 25. Staff and fiscal resources for these tasks will be considered and updated in a future Work Plan, unless there is interest to identify any of these tasks as an immediate priority to be added to the FY 25 Work Plan. Based on limited Staff resources, adding items to the FY 25 Work Plan will require removing other priorities.

## Slide 53
Project | Page
County Early Childcare/Education LDR Amendments | 55
Town Sign Standards Update | 56
Town Review of Character Change in Stable and Transitional Districts | 57
County Development Exactions Update | 58
Town Lodging and Short Term Rental Review Phase II | 59
Town Natural Resource LDRs | 60
Joint Local Connectors Capital Project Group 4 Charter/Concept Design East West Connector | 61
Town of Jackson DEI Phase I work | 62
Update of Legacy Zoning Prioritization Areas | 63
Future Tasks – Non-Budgeted and/or Unscheduled

## Slide 54
County Early Childcare/Education LDR Amendments
Comp Plan Strategies:
Policy 4.2.b Promote a balanced mix of nonresidential uses.
Policy 6.3.e. Balance housing, nonresidential development, and civic uses
Policy 8.1.b Coordinate with independent service providers
Task: The County has included looking at supporting early childcare and education as a part of the 2023 Areas of Focus discussion. This topic includes work from multiple departments through creation of an action plan and ultimately lead to a recommendation for future LDR amendments. This component of the areas of focus includes researching the Land Development Regulations to understand where childcare is currently allowed, where the barriers exist, outreach with stakeholders to understand community barriers, and possible amendments to the LDRs to facilitate childcare as a result.
Status: This task has not yet begun.
Progress | 0% To be Determined Long-Range Planning | 
Timeframe |  | 
Task Lead |  | 
Resources | FY 25+ | Total
Consultant Services | TBD | TBD
Long Range Planning | 300 hrs | 300 hrs
County Planning Director | 20 hrs | 20 hrs
FY 25+

## Slide 55
Town Sign Standards Update
Comp Plan Strategies:
3.2.S.6: Evaluate and update design regulations to encourage quality public space.
Task: Update Town sign standards to fix inconsistencies and deficiencies in current standards created by emergency LDR amendment required by federal law. In addition, make overdue improvements to design and materials standards and permitting procedures.
Status: This task has not yet been started and based on recent Council input it will not begin sooner than FY26.
Progress | 0% July 2025 – July 2026 Town Planning |  | 
Timeframe |  |  | 
Task Lead |  |  | 
Resources | FY 23 | FY 25+ | Total
Long-Range Planning | 0 hrs | 10 hrs | 10 hrs
Town Planning | 0 hrs | 50 hrs | 50 hrs
Town Planning Director | 0 hrs | 130 hrs | 130 hrs
FY 25+

## Slide 56
Town Review of Character Change in Stable & Transitional Districts
Comp Plan Strategies:
Policy 3.2.a Enhance Quality, Desirability and Integrity of Complete Neighborhoods - This Policy is in place for stable neighborhoods which may “be enhanced by infill that is consistent with existing patterns and scale of development and includes additional amenities to make the most appropriate places for development more enjoyable places to live.” Many developed neighborhoods are seeing a shift in character as many infill projects include purchase of an older residence, tear down, and re-build with a much larger structure.
3.3.b Provide predictability in land use decisions – Updating these regulations may increase predictability by all including landowners wishing to complete infill development, and neighbors to said development so that folks can generally expect what to see as the result of additional infill being constructed.
3.3.e Preserve historic Structures and Sites – While this Policy speaks to preservation of historic structures, much of a historic building also includes the character of the site around it. New infill development adjacent to historic sites must consider existing character and how the new development will fit within the historic context of the existing neighborhood.
4.1.c. Promote Compatible Infill and Redevelopment that fits Jackson’s neighborhoods – “…redevelopment will be compatible in scale, use and character in Stable Subareas…”
Task: Review the Town stable and transitional residential areas regarding desired community character compared to observed and data-based recent changes. Data collection and analysis has been completed and LDR amendments are being considered.
Status: This item was postponed by the Council until at least FY26 at which time this project will be evaluated again for possible inclusion in the Work Plan.
Progress | 30% July 2025 – July 2026 Community Development Director |  |  | 
Timeframe |  |  |  | 
Task Lead |  |  |  | 
Resources | FY 22 | FY 23 | FY 25+ | Total
Town Planning Director | 30 hrs | 5 hrs | 5 hrs | 40 hrs
Town Com. Dev. Director | 60 hrs | 5 hrs | 0 hrs | 65 hrs
Housing Department | 10 hrs | 0 hrs | 0 hrs | 10 hrs
FY 25+

## Slide 57
County Development Exactions Update
Comp Plan Strategies:
Policy 10.2b Use adaptive management to ensure we are achieving our vision.
Task: Contract with a consultant to complete a nexus study to update the County’s development exaction requirements. Currently, the County requires exactions (land dedication or a fee in lieu) for the school district and parks to offset the impacts of residential development that increases the need for these services. The objective of this task is to evaluate the current nexus between residential development and the induced need for these services to ensure that the exaction requirement is accurate. Also, this task will explore moving from an exaction requirement to an impact fee requirement that more comprehensively accounts for development impacts to schools and parks, but also other important community services such as Fire/EMS, law enforcement, road maintenance, etc.
Status: This task has not yet begun.
Progress | 0% To be Determined Long-Range Planning | 
Timeframe |  | 
Task Lead |  | 
Resources | FY 25+ | Total
Consultant Services | TBD | TBD
Long Range Planning | 200 hrs | 200 hrs
County Planning Director | 20 hrs | 20 hrs
FY 25+

## Slide 58
Town Lodging & Short Term Rental Review Phase II
Comp Plan Strategies:
4.2.S.5: Review the Lodging Overlay boundary and associated regulations and incentives to determine the desired location, type and size of lodging.
Task: Upon completion of Phase 1: Data Collection and Review, Council will determine the appropriate next step. Staff have described below four (4) possible alternatives that could be considered by Council upon completion of Phase 1.
Alternative 2a: Review of the Amount, Location and Type of Lodging
  Scope: This alternative would be similar to the initiative undertaken by the Town in 2012-13 as described above which looked at the desired location of and type of lodging in the community based upon a lodging overlay district.
  Outcomes: Potential outcomes of this effort would be changes to the current lodging overlay boundaries and types of lodging uses allowed therein
  Timeframe: 12 months as this would include a public process with a lot of public engagement
Alternative 2b: Amendments to the LDRs based upon the current lodging overlay and current allowed uses
  Scope: Consideration of potential LDR amendments within the current lodging overlay boundary (no changes) to address issues identified during review of development over the past 10 years and consistency with the Comprehensive Plan including but not limited to:
  Size of individual units, buildings and facilities
  Mix of lodging types, i.e., short term rental and conventional lodging, timeshare, fractional, etc.
  Outcomes: Potential outcomes of this effort would be amendments to the current LDRs
  Timeframe: 6 months, including public hearing process at Planning Commission and Town Council
Alternative 2c: Amendment to the Comprehensive Plan regarding Lodging and LDR amendments
  Scope: Consider what role lodging should play in the community town and/or town/county different from what is currently envisioned
  Outcomes: Possible amendment to the Comprehensive Plan
  Timeframe: 12-18 months, including a Comprehensive Plan and LDR amendments as this would include a public process with a lot of public engagement and joint consideration by the Town and County
Alternative 2d: No further action taken at this time, continue to monitor lodging development only
  Scope: Retain current Comprehensive Plan and LDRs
  Outcomes: Continued monitoring
  Timeframe: 2 months, no public involvement
Status: This task has not begun and the timeframe is TBD based on workloads.
Progress | 0% TBD Town Planning | 
Timeframe |  | 
Task Lead |  | 
Resources | FY25 | Total
Consulting Services | TBD | TBD
Town Planning Director | TBD | TBD
Town Com. Dev. Director | TBD | TBD
Town Planning | TBD | TBD
Housing Department | TBD | TBD
FY 25+

## Slide 59
Town Natural Resource LDRs
Comp Plan Strategies:
1.1.S.3: Establish a monitoring system for assessing the impacts of growth and development on wildlife and natural resources. Implement actions in response to what is learned to provide better habitat and movement corridor protection.
1.1.S.4: Evaluate and amend wildlife protection standards for development density, intensity, location, clustering, permeability and wildlife-human conflict.
1.1.S.5: Evaluate mitigation standards for impacts to critical habitat and habitat connections and update as needed.
1.1.S.6: Identify areas for appropriate ecological restoration efforts.
1.2.S.1: Evaluate and update natural resource protection standards for waterbodies, wetlands and riparian areas.
1.2.S.2: Evaluate and update surface water filtration standards, focusing on developed areas near important waterbodies.
4.4.S.5: Develop a Flat Creek Corridor Overlay to addresses the ecological, recreational, and aesthetic values of the corridor, while respecting the existing uses and/or property rights along the corridor.
Task: Update Town natural resource protection LDRs based on the update to the County natural resource protections update. Utilize a series of small projects, such as stormwater quality regulations, Flat Creek protections, etc. to update the Town’s natural resource protections.
Status: This task will begin when the County Natural Resource Regulations have been completed. It may alternatively be addressed through corridor plans and water resource protections.
Progress | 0% After completion of County Natural Resource LDRs Long-Range Planning
Timeframe | 
Task Lead | 
Resources | To be determined
FY 25+

## Slide 60
Joint Local Connectors Capital Project Group 4/Concept Design Northern South Park East-West Connector
ITP Action Items: Chapter 4, Transportation Demand Management: Establish a TDM Program.
Task: These projects will be planned and designed to serve travel to, from and within Jackson Hole and to improve connectivity between local neighborhoods. The RTPA FY2024 budget included $150,000 to carry out public engagement and develop high-level conceptual plans for a transportation network that meets the goals of the Comprehensive Plan and serves the approved developments in West Jackson (areas west of US89 bound by South Park Loop road to the North and west and Red House Road to the south). The resulting plans and preliminary concepts could be used to understand potential transportation infrastructure needs if directed by BCC/Council.
Status: Transportation planning and modeling work has been completed as part of Neighborhood Plan for Northern South Park. The East West Connector will be dependent upon the phasing of the buildout of the planning area and obtaining necessary easements. The Modernizing Mobility for West Jackson study is underway: https://modernizingmobility.konveio.com/
Progress | 1%
Timeframe | Now – January 2024
Task Lead | Long-Range Planning
Resources | RTPA- 200 hours
FY 25+

## Slide 61
Phase I Diversity Equity & Inclusion Amendments
Comp Plan Strategies:
Strategies would be created for the Comprehensive Plan out of this process.
Task: Recommendation for Town Council to work with County Commission to direct staff to add a chapter to the Comprehensive Plan focused on equity: The Equity Task Force (ETF) recommends that Town Council direct staff to update the Comprehensive Plan (Comp Plan) to include a chapter about Equity under the ‘Quality of Life’ Common Value.
Status: This task has not yet begun.
Progress | 0% To be Determined To be Determined | 
Timeframe |  | 
Task Lead |  | 
Resources | FY 25+ | Total
Consultant Services | TBD | TBD
Long Range Planning | TBD | TBD
County Planning Director | TBD | TBD
Town Community Development Director | TBD | TBD
Town Planning | TBD | TBD
Community Development Staff | TBD | TBD
FY 25+

## Slide 62
Update of Legacy Zoning Prioritization Areas
Comp Plan Strategies:
3.2.S.1: Update zoning and land development regulations within Complete Neighborhoods to achieve the desired character for Complete Neighborhoods as established in Character Districts
3.2.S.2: Identify locations for locally-oriented and visitor-oriented nonresidential uses within Complete Neighborhoods based on the Character Districts.
3.2.S.3: Update land development regulations for nonresidential areas within Complete Neighborhoods to encourage ground floor vitality and flexible mixed use.
3.2.S.5: Evaluate and update regulations in Complete Neighborhoods to allow and promote the appropriate variety of housing types identified through the Character Districts.
3.2.S.6: Evaluate and update design regulations to encourage quality public space.
6.2.S.3: Maintain locations for light industry, and evaluate and update regulations relating to live-work light industry opportunities.
6.3.S.2: Evaluate and update land use regulations to foster a positive atmosphere and attract appropriate types of business to the community. Promote the types of uses that provide middle income jobs and promote entrepreneurship.
Task: In the last few years, the County has updated some of its legacy zoning in specific areas: the Aspens residential areas and in the Hog Island area. Moving forward, there may be interest in identifying the next key area for rezoning. This could include residential areas around Wilson, Kelly, Alta, or around the South Park area. The updates would look at rezoning legacy Rural or Complete Neighborhood areas, and a prioritization of where to start first would be needed. In order to determine priority, Staff would need to spend some time investigating the current zoning configurations and analyzing the need based on area to form a formal recommendation regarding prioritization of the next areas to rezone.
Status: This task has not yet begun.
Progress | 0% To be Determined Long-Range Planning
Timeframe | 
Task Lead | 
Resources | FY 25+
Consultant Services | TBD
Long Range Planning | TBD
County Planning Director | TBD
FY 25+

## Slide 63: Completed Work Plan Tasks
The following section includes is a list of the implementation work completed or substantially completed since Comp Plan adoption in 2012 to date.

## Slide 64
Comprehensive Plan Implementation |  | 
Task | Date Complete | Comp Plan Strategies Implemented
Land Development Regulation Updates/Studies |  | 
Town Municode Implementation |  | 
Town LDR Cleanup |  | 
Northern South Park Implementation LDRs | March 2024 | 3.3.S.5
Joint Standardized Indicator Data Collection – Smart Gov | April 2022 | Principle 9.2
Northern South Park Neighborhood Plan | July 2022 | 3.3.S.5
County Hog Island LDR and Zoning Map Amendment | April 2022 | 3.2.S.1
County Wildlife Feeding & Bear Conflict LDR Update | April 2022 | 1.1.S.4
Housing Nexus Study | April 2022 | 5.3.S.1
Housing Nexus Study | October 2013 | 5.3.S.1
Vegetation Mapping | December 2013 | 1.1.S.1
Joint LDR Restructure | December 2014 | 3.3.S.2, 3.3.S.3
County Rural LDRs Updates | December 2015 | 1.4.S.1, 1.4.S.2, 1.4.S.3, 3.1.S.1, 3.1.S.2, 3.3.S.2, 3.3.S.3
Town District 2 and LO Zoning | November 2016 | 4.1.S.1, 4.2.S.2, 4.2.S.4, 4.2.S.6, 4.4.S.3, 4.4.S.4
Focal Species Study | April 2017 | 1.1.S.2
Nonconformities LDRs Cleanup | May 2016 | 3.3.S.2, 3.3.S.3
County Nuisance LDRs | July 2016 | 3.1.S.1, 3.2.S.2
Town Adult Entertainment LDRs | March 2017 | 3.2.S.1
Exterior Lighting LDRs Update | September 2016 | 1.3.S.2
Town ARU Allowance | November 2016 | 5.2.S.2
Wildland Urban Interface LDRs | December 2016 | 3.4.S.2, 3.4.S.3
2016 LDR Cleanup | January 2017 | 3.3.S.2, 3.3.S.3
Housing Mitigation LDRs | July 2018 | 5.1.S.1, 5.2.S.2, 5.3.S.2, 5.4.S.3, 5.4.S.4
Town District 3-6 Zoning | July 2018 | 4.1.S.1, 4.1.S.2, 4.2.S.4, 4.3.S.1, 4.4.S.3, 5.2.S.1, 5.4.S.3, 5.4.S.4
County Natural Resource LDRs | 75% complete | 1.1.S.3, 1.1.S.4, 1.1.S.5, 1.1.S.6, 1.1.S.7, 1.2.S.1, 1.2.S.2
Joint Comprehensive Plan Review (GMP) | November 2020 | Policy 9.1.a and 9.1.d
LDR Cleanup | July 2020 | 3.3.S.2, 3.3.S.3
Hog Island Zoning Update | March 2022 | 
Wildlife Friendly Fencing Update | November 2021 | 1.1.S.4

## Slide 65
Comprehensive Plan Administration |  | 
2012 Work Plan | June 2012 | Principle 9.2
2013 Indicator Report & Work Plan | May 2013 | Principle 9.2
Standardize Data Collection | 70% complete | Policy 9.2.a
2014 Indicator Report & Work Plan | May 2014 | Principle 9.2
2015 Indicator Report & Work Plan | August 2015 | Principle 9.2
2016 Indicator Report & Work Plan | April 2016 | Principle 9.2
2017 Indicator Report & Work Plan | April 2017 | Principle 9.2
2018 Indicator Report & Work Plan | April 2018 | Principle 9.2
2019 Indicator Report & Work Plan | April 2019 | Principle 9.2
2020 Indicator Report & Work Plan | April 2020 | Principle 9.2
2021 Indicator Report & Work Plan | May 2021 | Principle 9.2
2022 Indicator Report & FY 23 Work Plan | April 2022 | Principle 9.2
2023 Indicator Report & FY 24 Work Plan | April 2023 | Principle 9.2
Joint Comprehensive Plan Review (GMP) | November 2020 | Policy 9.1.a and 9.1.d
Joint Public Engagement | Continuous | 3.3.S.1
Other Coordination | Continuous | 
Integrated Transportation Plan (ITP) Implementation |  | 
ITP | September 2015 | 7.1.S.1, 7.1.S.4, 7.1.S.6, 7.1.S.8, 7.1.S.9
Town Community Streets Plan | April 2015 | 7.2.S.1
Town District 3-6 Parking Study | December 2017 | 4.1.S.1, 4.1.S.2, 5.4.S.3, 7.3.S.1
Joint Regional Traffic Model | January 2019 | 7.2.S.6
Downtown Parking Study | July 2019 | 4.1.S.1, 4.1.S.2, 5.4.S.3, 7.3.S.1
ITP Technical Update | December 2020 | 7.1.S.1, 7.1.S.4, 7.1.S.6, 7.1.S.8, 7.1.S.9
ITP Transportation Lead | February 2022 | 

## Slide 66
Housing Action Plan Implementation |  | 
Housing Action Plan (HAP) | November 2015 | 5.4.S.1, 5.4.S.2
Housing Authority Restructure | December 2016 | HAP: 1
2016 Housing Supply Plan | October 2016 | HAP: 2
Housing Rules and Regulations | July 2018 | HAP: 3B
2017 Housing Supply Plan | November 2017 | HAP: 2
2018 Housing Stock Portfolio | 75% complete | HAP: 2F
Online Intake Form | February 2018 | HAP: 2F, 3C, 4B
2018 Housing Supply Plan | June 2018 | HAP: 2
2019 Housing Supply Plan | April 2019 | 5.4.S.1
2020 Housing Supply Plan | January 2020 | 5.4.S.1
2022 Housing Needs Assessment | March 2022 | 
Sustainability |  | 
Town Wastewater Treatment Plant Technical Review | November 2022 | Principle 1.2, Policy 3.3.d, 8.1.5.3
County Water Quality Management Plan | April 2024 | 1.2.S.3, 1.2.S.5, 1.2.S.6, Chapter 8